## Start Here
SQA MANUAL TESTING TRACKER — START HERE
Purpose | Track your manual testing practice for the e-commerce website.
How to use | Upload this .xlsx file to Google Drive, then right-click → Open with → Google Sheets.
1. Test Plan | Fill in project details, scope, tools, environment, risks, and timeline.
2. Test Scenarios | List high-level features or things you want to test.
3. Test Cases | Write steps and expected results; after testing, update actual result and status.
4. Bug Log | Log only issues you actually observe. Include steps, expected/actual result, severity, and status.
5. Summary | Counts automatically update from the Test Cases and Bug Log sheets.
Status meanings | Not Run = not tested; Pass = matches expected; Fail = differs; Blocked = unable to test.
Practice URL | http://127.0.0.1:5000
Practice login | Email: tester@example.com ¦ Password: Test123!
Important | Keep your local server running while testing. Do not record an example as a real bug unless reproduced.

## Summary
MANUAL TESTING SUMMARY
Metric | Count | How to interpret
Total test cases | 9 | Number of test case IDs entered
Pass | 0 | Tests that met expected result
Fail | 0 | Tests that did not meet expected result
Blocked | 0 | Tests unable to execute
Not Run | 9 | Tests not executed yet
Total bugs logged | 7 | Bug IDs entered in Bug Log
Open bugs | 7 | Bugs not yet resolved

## Test Plan
Field | Details / Your Update
Project Name | Manual Testing Practice E-commerce Website
Prepared By | Enter your name
Version | 1.0
Date Created | Enter date
Objective | Verify that the website's main functions work as expected.
In Scope | Home, products/search/filter, login/logout, cart, checkout form, contact form.
Out of Scope | Real payment gateway / real online transactions.
Test Approach | Manual functional, smoke, negative, UI, and regression testing.
Test Environment | Windows + Google Chrome + http://127.0.0.1:5000
Tools | Chrome for testing; Google Sheets for test cases/results; Jira optional for bugs.
Entry Criteria | Website runs; pages are accessible; test data is ready.
Exit Criteria | Planned tests executed or blockers documented; results and defects recorded.
Risks / Assumptions | Local server must remain running; no real payment processing.
Planned Start Date | Enter date
Planned End Date | Enter date
Notes / Updates | Add ongoing updates here.

## Test Scenarios
Scenario ID | Feature / Module | Test Scenario | Priority | Status | Notes
TS-001 | Home | Verify home page loads and main navigation works | High | Not Run
TS-002 | Products | Verify product list displays correctly | High | Not Run
TS-003 | Search / Filter | Verify product search and price filters | Medium | Not Run
TS-004 | Login | Verify login with valid credentials | High | Not Run
TS-005 | Login | Verify login rejects invalid credentials | High | Not Run
TS-006 | Logout | Verify user can log out | Medium | Not Run
TS-007 | Cart | Verify adding products and changing quantity | High | Not Run
TS-008 | Cart | Verify cart total updates correctly | High | Not Run
TS-009 | Checkout | Verify required checkout fields and submission | High | Not Run
TS-010 | Contact | Verify contact form validation and submission | Medium | Not Run

## Test Cases
Test Case ID | Scenario ID | Module | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Executed By | Execution Date | Bug ID | Evidence / Notes
TC-001 | TS-001 | Home | Verify home page loads | Local server is running | 1. Open http://127.0.0.1:5000 | N/A | Home page loads without an error |  | Not Run | High
TC-002 | TS-002 | Products | Verify product list displays | Website is open | 1. Click Products 2. Observe product list | N/A | Products are displayed with relevant details |  | Not Run | High
TC-003 | TS-003 | Search | Search for a product | Products page is open | 1. Enter a product name 2. Submit search | Use a visible product name | Relevant matching products are shown |  | Not Run | Medium
TC-004 | TS-004 | Login | Login with valid credentials | User is logged out | 1. Open Login 2. Enter email and password 3. Click Login | tester@example.com / Test123! | Login succeeds and logged-in state is shown |  | Not Run | High
TC-005 | TS-005 | Login | Login with wrong password | User is logged out | 1. Open Login 2. Enter valid email and wrong password 3. Click Login | tester@example.com / Wrong123! | Login is rejected and appropriate message/state is shown |  | Not Run | High
TC-006 | TS-007 | Cart | Add a product to cart | Products page is open | 1. Select a product 2. Click Add to Cart 3. Open cart | Any listed product | Selected product appears in cart with correct quantity |  | Not Run | High
TC-007 | TS-008 | Cart | Verify cart total | At least one product is in cart | 1. Note product price and quantity 2. Compare displayed total | Price × quantity | Cart total matches item prices and quantities |  | Not Run | High
TC-008 | TS-009 | Checkout | Validate required checkout fields | Cart contains a product | 1. Open checkout 2. Leave required fields blank 3. Submit form | Blank name/city/address | Required fields are validated and checkout is not completed |  | Not Run | High
TC-009 | TS-010 | Contact | Validate empty contact form | Contact page is open | 1. Leave required fields blank 2. Submit form | Blank required fields | Required field validation appears; form is not submitted |  | Not Run | Medium

## Bug Log
Bug ID | Title / Summary | Module | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Date Reported | Assigned To | Test Case ID | Screenshot / Evidence | Retest Result | Notes
BUG-001 | Contact form accepts malformed email address | Contact | Chrome / http://127.0.0.1:5000 | Contact page is open | 1. Open Contact page. 2. Enter name and message. 3. Enter malformed email such as x@@example.com. 4. Submit. | Form should reject malformed email and show validation message. | Code review candidate: validation only checks that email contains @ and that the part after the last @ contains a dot; malformed values like x@@example.com may be accepted. Reproduce in browser. | Moderate | Medium | New | QA Tester | 2026-10-25 |  | TC-009 |  | Not Retested | Candidate from source-code review; confirm manually before reporting as verified.
BUG-002 | Cart quantity can exceed maximum of 99 when adding repeatedly | Cart | Chrome / http://127.0.0.1:5000 | A product is available on Products page | 1. Open Products. 2. Add the same product with quantity 99. 3. Add that same product again with quantity 1. 4. Open Cart. | Cart quantity should remain within the documented maximum of 99, or the app should clearly prevent exceeding it. | Code review candidate: Add-to-cart adds the new quantity to the existing quantity without checking the combined total; cart may show 100 or more. Reproduce in browser. | Moderate | Medium | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Candidate from source-code review; confirm manually before reporting as verified.
BUG-003 | Logout action uses GET request | Authentication | Chrome / http://127.0.0.1:5000 | User is logged in | 1. Log in. 2. Observe the Logout link/request. 3. Open the logout URL directly in the browser. | State-changing logout should use POST with appropriate CSRF protection, rather than a GET link. | Code review finding: /logout is implemented as a GET route and clears the session. This is a security design issue; verify the UI flow and document as a security finding. | Major | Medium | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Security-oriented finding from source-code review; not yet manually verified.
BUG-004 | Login redirect may send user to an external URL | Authentication | Chrome / http://127.0.0.1:5000 | User is logged out | 1. Open /login?next=https://example.com. 2. Log in using tester@example.com / Test123!. 3. Observe the destination after login. | After login, user should be redirected only to a trusted local page. | Code review candidate: login redirects to the supplied next parameter without validating that it is a local URL. Test only with a harmless external URL and record the result. | Major | Medium | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Potential open-redirect security issue from source-code review; confirm manually.
BUG-005 | Unauthenticated user can add products to cart | Cart / Authentication | Chrome / http://127.0.0.1:5000 | User is logged out and Products page is available | 1. Log out or open the site in a fresh/incognito session. 2. Open Products. 3. Click Add to Cart for any product. 4. Open Cart. | Per the requested business rule, redirect the user to Login/Sign Up before allowing cart actions, or clearly enforce authentication before continuing. | Source-code review confirms /cart/add/<product_id> does not check login session, so a logged-out visitor can add an item. Reproduce in browser. | Major | High | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Verified from app.py route logic; reproduce in browser and attach screenshot before treating as fully verified.
BUG-006 | Unauthenticated user can proceed to checkout and place an order | Checkout / Authentication | Chrome / http://127.0.0.1:5000 | User is logged out and cart contains at least one product | 1. Log out or open a fresh/incognito session. 2. Add a product to cart. 3. Open Cart. 4. Click Checkout. 5. Enter name, city and address. 6. Submit the order. | Per the requested business rule, user must be logged in before checkout/order placement; if this is a first-time user, show Sign Up and then Login. | Source-code review confirms /checkout checks only whether cart is empty and required checkout fields are filled; it does not require login. An unauthenticated visitor can submit a demo order. Reproduce in browser. | Major | High | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Potentially confirmed from app.py route logic; verify the full UI flow and capture evidence.
BUG-007 | New visitors cannot create an account because Sign Up is unavailable | Authentication / Registration | Chrome / http://127.0.0.1:5000 | Visitor has never registered and is logged out | 1. Open the website. 2. Open the Login page. 3. Look for a Sign Up / Create Account option. 4. Try to register a new account. | If registration is required by the product requirements, a new visitor should be able to create an account, then log in before using cart/checkout. | Source-code review shows only a hard-coded demo user and no registration route/template. A new visitor cannot create an account through the UI. | Major | High | New | QA Tester | 2026-10-25 |  |  |  | Not Retested | Classify as a bug only if Sign Up is part of the agreed requirements; otherwise record as a missing feature/enhancement.